## Tabelle1
| Sarkovic | Fritz | Weiler
2017-09-22 | Mockups. | Sprints and description. | Github Connection Visual Studio and Android Studio.
2017-09-29 | Android Login/Registration GUI first draft finished. | C# Login/Registration first draft finished. Check of valid inputs. | ERD and LM finished.
2017-10-06 | Android Main GUI first draft; Pupil and Database class | C# Registration: checks if values are correct | Research MongoDB
2017-10-13 | Android Login bugs fixed | C# MainWindow with Menu finished; AddEntryWindow finished | Research MongoDB (not finished), Virtual Machine (Aphrodite? Not finished)
2017-10-20 | Android AddEntryWindow finished (90%) | C# AddEntry: checks if values are correct finished (100%) | Virtual Machine bug fixed. MongoDB locally installed; Table company created
2017-10-27 | Android AddEntryWindow Bug fixing (100%) | C# List of Entries and research google maps (location) (30%) | MongoDB in Virtual Machine installation finished (60%)
2017-11-03 | Android Research connection MongoDB with AndroidStudio (20%) | C# GoogleMaps in WebBrowser (50%) | MongoDB locally adapted (80%).
2017-11-10 | Android Creation of remaining activities, MongoDB jar added, connection in progress (40%) | C# GoogleMaps WebBrowser dynamically added. 2nd column in progress (70%). | MongoDB installation aphrodite "finished" (Mr. Oberlercher adapts aphrodite) (99%). Research and queries for the collections (40%)