## Tabelle1
| Sarkovic | Fritz | Weiler
2017-09-22 | Mockups. | Sprints and description. | Github Connection Visual Studio and Android Studio.
2017-09-29 | Android Login/Registration GUI first draft finished. | C# Login/Registration first draft finished. Check of valid inputs. | ERD and LM finished.
2017-10-06 | Android Main GUI first draft; Pupil and Database class | C# Registration: checks if values are correct | Research MongoDB
2017-10-13 | Android Login bugs fixed | C# MainWindow with Menu finished; AddEntryWindow finished | Research MongoDB (not finished), Virtual Machine (Aphrodite? Not finished)
2017-10-20 | Android AddEntryWindow finished (90%) | C# AddEntry: checks if values are correct finished (100%) | Virtual Machine bug fixed. MongoDB locally installed; Table company created
2017-10-27 | Android AddEntryWindow Bug fixing (100%) | C# List of Entries and research google maps (location) (30%) | MongoDB in Virtual Machine installation finished (60%)
2017-11-03 | Android Research connection MongoDB with AndroidStudio (20%) | C# GoogleMaps in WebBrowser (50%) | MongoDB locally adapted (80%).
2017-11-10 | Android Creation of remaining activities, MongoDB jar added, connection in progress (40%) | C# GoogleMaps WebBrowser dynamically added. 2nd column in progress (70%). | MongoDB installation aphrodite "finished" (Mr. Oberlercher adapts aphrodite) (99%). Research and queries for the collections (40%)
2017-11-17 | Android Connection MongoDB finished (100%), Company Class created, tried to convert collection of mongoDb to list (30%) | C# WebBrowser dynamically adding, still no reasonable way. Connection to MongoDB in order to get the entries: Filename too long. Probably change of directory needed (75%) | MongoDB aphrodite adapted (100%). Collection finished (100%). Inserts in Collection (20%)
2017-11-24 | Android Get collection (documents) of mongoDB doesn't work. Null error (but connection is ok) (40%). | C# Displaying entries works (100%). Login works (100%). | MongoDB Inserts finished (100%)
2017-12-01 | Android Get collection "works" (however, only in javafx => creating webservice in javafx to get data in android) (50%) | C# Admin Login: additional menuItem with onClickListener appears. New entries have to be loaded, in order to accept them (50%) | WebService with one collection of mongoDB. Creation together with Sarkovic (50%)
2017-12-08 | WebService get collection pupil and entry (90%). | C# Admin Login: multiple columns in listview with buttons and images (to accept a new entry). Multiple Google Maps (Location of Company) through wrapper class. Both functions without mongoDB (100%) | WebService get collection pupil and entry (90%).
2017-12-15 | WebService get collection pupil works (100%), adapted java classes, adapted Database methods (40%) | WebService Login both Pupil and Teacher works, get all Entries works, join in mongoDB (helped Weiler) (50%) | WebService get collection pupil works (100%), added java Classes Pupil and Entry, join in MongoDB works in Console (50%)
2017-12-22 | Android getEntries of WebService works (50%) | C# getAllEntries of WebService works but no MongoId and Date = 0000.00.00 ? (50%) | Android getEntries of WebService (100%)
2018-01-12 | Android display of all entries (50%) | MongoDb update of wrong entry. WebService bugfix Entries date (50%) | MongoDB restore (MongoDB lost all its data). WebService bugfix MongoId (Store as String) (50%)
2018-01-19 | Android display of all entries (80%) | C# Load admin gui elements in combination with webservice. (50%) WebService bugfix Entries date (100%), however new bug: "no document validation" | Research Web App Frameworks, decision: JSF, reading up in JSF (10%), WebApp Login (100%), Display of all entries (100%), AddEntry (100%)
2018-02-23 | Android display of all entries (100%). Communication of start- and enddate between two activities (30%) | C# LoadAdminGuiElements in combination with webservice (100%). Implementation of adminNote in all windows (40%) | Reading up in JSF (100%), Restore of MongoDB (it was empty) (100%), MongoDB adminNote added (100%)
2018-03-02 | Android communication of start- and enddate between two activities (100%) | C# Login with active directory of school (100%), Admin note (90%) | WebApp detailed display of entries and option to edit (detailed display 100%)(edit entry 50%)