## Tabelle1
| Sarkovic | Fritz | Weiler
2017-09-22 | Mockups. | Sprints and description. | Github Connection Visual Studio and Android Studio.
2017-09-29 | Android Login/Registration GUI first draft finished. | C# Login/Registration first draft finished. Check of valid inputs. | ERD and LM finished.
2017-10-06 | Android Main GUI first draft; Pupil and Database class | C# Registration: checks if values are correct | Research MongoDB
2017-10-13 | Android Login bugs fixed | C# MainWindow with Menu finished; AddEntryWindow finished | Research MongoDB (not finished), Virtual Machine (Aphrodite? Not finished)
2017-10-20 | Android AddEntryWindow finished | C# AddEntry: checks if values are correct | Virtual Machine bug fixed. MongoDB locally installed; Table company created